**Warcop Parish Council Action Plan 2018 - 2019**

Serving the communities of Bleatarn, Coupland Beck, Sandford & Warcop - Visit: [www.warcop.org.uk](http://www.warcop.org.uk)

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Required Outcome** | **Actions** | **Lead** | **Partners** | **Cost** | **Funding Source(s)** | **Who will Monitor & Evaluate****Progress?** | **Priority 1, 2 3****(1 = highest)**  |
|  | **Flood Risk Reduction Phase 2 - Work with The Woodland Trust, Eden Rivers Trust and the MOD on upstream project(s)** | **Upstream water diversion options. Continue to seek funding to achieve this.**Repair & paint railings by Crooks Beck – Completed Summer 2018 | **DK****??****DK** | EAEden Rivers TrustWoodland TrustEA or local volunteers | Unknown | EAEden Rivers TrustWoodland TrustParish CouncilCCC Highways repaired posts & paint | PCEA | **1** |
|  | **Refine new grass-cutting arrangements** **Maintain cemetery, churchyard & Parish Hall to a high standard** | Repair fallen walls, cut back trees, maintain footpaths and so on. | **TW****All** | Volunteers | ServicingFuelStorage rental£200 pa | PC reserveChurchyard/cemetery maintenance fund in budget | PCCH/DK | 1 |
|  | **Continue to improve the Parish, including seeking grant-funding for Project Development****e.g. Cumbria Community Foundation Flood Recovery Funds****Support the work of Warcop Parish Hall****Allocate annual maintenance budget for churchyard and cemetery to maintain walls, trees etc.****Parish Hall – Village Footpath Project. Keep under review until land access can be agreed.****Maintain War Memorial which now has Grade II listed status from September 2018****Achieve Superfast broadband for Sandford a.s.a.p.****Contribute to the Upper Eden Community Plan consultation** | **Identify person to apply for appropriate grants**Erect fencing of Warcop village green, new play equipment, new benchesSeek views of Sandford and other residents for improvements thereReport issues with potholes, lighting, public footpathsReduce dog-fouling – more signs and leaflet dropSuccessful Bid to EDC Members’ FundPC to assess cemetery and churchyard condition annually and arrange for any remedial work to be doneApply for funding of next stage of path from Parish Hall to village **– Review this project**Improve War MemorialPosts, chain, gravel repaired and painted Oct 2018**Achieved spring 2019**As time & capacity allows | **TW****GF/JH****DK****DK****DK/CH****TW****DK****All****DK/TW** | EDC/ACT/Cumbria CVSCCC HighwaysWarcop WebsiteEDCPCCAllVolunteers/MaxConnecting CumbriaRory StewartT&B | Annual donation for specific items or projects£500 pa**£1502****c. £14,000** | PC precept fundsEDCPC preceptEDC Members’ FundPC FundsConsider whether to return grantCost of new posts and painting chain and kerb stones c £100None | PCPC | 121213 |
|  | **Develop a Woodland Burial Site in Warcop Cemetery and all necessary guidance** | Write guidance leafletDemarcate area and signageHedging plants planted 2019 and sign erected for separate woodland area within cemetery. Gate to be erected when hedge matures.Clerk to keep record of plots.New Cemetery noticeboard and directing people to use waste bin on Cemetery Lane | **DK** | EDC |  | PC funds | PC | 2 |
|  | **Continue to improve road safety: A66, potholes, speed limits.****Adopt footway lighting from EDC****Support minibus Link Service from Warcop via Sandford to Appleby 563 Service** | Dualling of the A66 announced Nov 2016More actions to enforce 50mph limitImproved junctions at Flitholme and LangriggAttend Friends of Eden Valley Public Transport Group meetingsFully participate in all consultations and seek views of local residents. Meet Highways England where necessary.Done in 2018. Identify running costs and ask for LED upgradesSeek clarification on CCC’s offer of taking over lightingSupport Warcop/Sandford link to Stagecoach 563 serviceEncourage more passenger usage from our Parish | **DK****DK/TW****DK****DK****All****All****All****DK/All** | Highways EnglandEDCCCCCCCLocal Town & Parish CouncilsFriends of Eden Valley TransportAppleby Heritage CentreEDCCCCAppleby Heritage CentreCCC Rural Wheels  |  | Highways England | PC | 1112121 |
|  | **Continue to ensure that Appleby Horse Fair arrangements are adequate to minimise disruption** | Monitor pre-Fair period and address any issues in ParishAttend meetings of Upper Eden ForumMaintain contacts with travellers and police | **All** | MASCGKS & Appleby Neighbourhood ForumsPolice |  |  | PC | 1 |
|  | **Securing a viable future for The Chamley Arms as an important community asset.** | Pub purchased in 2019 and plans to redevelop it are in hand. Contact new owner to offer support and offer to meet with PC membersDiscuss potential options with local residents | **DK****DK** | EDCDeveloperCAMRA |  |  | Letter requesting update sent to EDC | 12 |
|  | **Involve & seek the views of the local community more regularly and publicise widely** | PC members attend monthly Coffee Mornings for drop-in sessions?Warcop website promoted and updated regularlyCreate mailing list for whole Parish to communicate directly with residentsPublicise in The WaySurveys on some issues | **DK** | WebsiteFacebookParish HallChurchesSchoolWISurveys |  |  | PC | 3 |
|  | **Investigate provision of activities for young people in the parish, seek funding to provide trained organiser of activities and events.** | Consult with young people of primary and secondary Age (**COMPLETED** April 2017)Members of PC join small working groupNext steps | **?** | Active CumbriaGrantFinder  |  | Grant ApplicationsTo appoint Youth Leader & purchase equipment | PC | 3 |
|  | **Community Emergency Planning** | Seek views of local people and produce a Community Emergency Plan for Warcop and Sandford – other villages too? | **TBC** | CALC advice | **All** |  | PC | 2 |

**Updated 17th July 2019**